## Sheet1
Sprint No | Issue ID | Issue Description | Comments | Fixed By | Tested on Dev | Tested on QA | Tested on Browser | Raised ticket | Notes | Defect Report Name. | After fix raised Ticket 2nd time. | Defect Report Name. | After fix raised ticket 3rd time | Defect Report Name. | After fix raised ticket 4th time | Defect Report Name. | Notes | After fix raised ticket 4th time | Notes
Sprint-77 | CARBON-79 | Spelling error on column title Transction in Billing History Accounts CSV download |  | Vivek | Working as expected | Working as expected | Google Chrome, IE 11, FireFox 46 | NA
| CARBON-85 | Searching for account issues in Leads section |  | Vivek | Working as expected | Working as expected | Google Chrome, IE 11, FireFox 46 | NA
| CARBON-169 | Balance Transfer 'Submit' issue in Finance tab |  | Vivek | Working as expected | Working as expected | Google Chrome, IE 11, FireFox 46 | NA
Sprint-78 | CARBON-103 | Sorting issue on Leads reports page for status column |  | Abhay | Working as expected | Working as expected | Google Chrome, FireFox. | NA
| CARBON-126 | "Duration" column sorting issue in "Call Tracking" section |  | Vivek | Working as expected | Working as expected | Google Chrome, FireFox. | NA
| AgileZen#325 | After editing partner in Valencia the list should remain as it is with the edited one. |  | Vivek | Working as expected | Working as expected | Google Chrome, FireFox. | NA
| CARBON-147 | Data missing on Billing History reports UI but present in downloaded CSV file. |  | Abhay | Working according to the ticket, but found a defect related to that page. | Working as expected | Google Chrome, FireFox. | Yes
| CARBON-94 | Sorting GUI Issues in Task Fulfillment and PPC Performance |  | Vivek | Found a defect in the ticket in its working. | Was not pushed to QA. | Google Chrome, FireFox. | Yes, Twice | Even after fixing it second time, the defect was reproduced. | Defect_Report_CARBON-94
| CARBON-328 | Lead Report Custom Date Range |  | Om | Found a defect in the ticket in its working. | Working as expected | Google Chrome, FireFox. | Yes |  | Defect_Report_CARBON-328
| CARBON-359 | Accounts Status Reordering |  | Abhay | Working as expected | Working as expected | Google Chrome, FireFox. | NA
| CARBON-356 | OS Valencia: Super Admin Highlight and Sort |  | Vivek | Partially tested. Raised query against the color chosen. | Basic functionality working as expected. | Google Chrome, FireFox. | NA
Sprint-79 | CARBON-365 | OS Carbon: Advertiser Account Welcome Email Content Change |  | Vivek | Working as expected |  | Google Chrome
| CARBON-367 | OS Carbon: Remove Main Partner from “Attach Partner Property” Dropdown | After fixing it after 4th time tested it on Harsh's VM.(do avoid rework) | Harsh | Found a defect in the working functionality of the page. |  | Google Chrome | Yes, discussed with client also. Found one more defect. | When you select one of partner accounts of safeguard then what should be the scenario. I.e what should you be able to view in the dropdown. | Defect_Report_CARBON-367 | Yes raised a ticket after fixing the defect 2nd time. | Defect_Report_CARBON-367 | Yes raised a ticket after fixing the defect 3rd time. | Defect_Report_CARBON-367_V2 | Yes raised a ticket after fixing the defect 4th time. | Defect_Report_CARBON-367_V3 | Even after testing it four times found a defect.
| CARBON-368 | OS Carbon: “Attach to Partner Property” Dropdown Permissions | After fixing it twice tested it on Harsh's VM.(do avoid rework) | Harsh | Found a defect in working functionality of the page. |  | Google Chrome | Yes, Twice. |  | Defect_Report_CARBON_368 | Yes raised a ticket after fixing the defect 2nd time. | Defect_Report_CARBON_368_V2
| CARBON-34 | Page keeps on loading when duplicate email id is entered. |  | Abhay | Working as expected | Working as expected | Google Chrome | Yes. But its not related to the expected working of ticket. Related to User page. |  | Defect_Report_CARBON-34
| CARBON-171 | Issue with editing account, State dropdown has no value and Country dropdown not proper. |  | Abhay | Working as expected | Working as expected | Google Chrome
| CARBON-148 | Filter by selection throwing error and not working properly on Import SEO Details under Tools tab |  | Vivek |  |  | Google Chrome
| CARBON-154 | Client Numbers: Existing client number should be edited/deleted without throwing any error | Was not able to reproduce as it was related to account which was deleted. | Vivek |  |  | Google Chrome | Yes. But its not related to the expected working of ticket. Related to another account on the same page. | While testing it with other scenarios could not find any client numbers under 74023, as they are already deleted. So not able to understand the actual working of the defect.