## Sheet1
Sprint No | Issue ID | Issue Description | Comments | Fixed By | Tested on Dev | Tested on QA | Tested on Browser | Raised ticket | Notes | Defect Report Name. | After fix raised Ticket 2nd time. | Defect Report Name. | After fix raised ticket 3rd time | Defect Report Name. | After fix raised ticket 4th time | Defect Report Name. | Notes | After fix raised ticket 4th time | Notes
Sprint-77 | CARBON-79 | Spelling error on column title Transction in Billing History Accounts CSV download |  | Vivek | Working as expected | Working as expected | Google Chrome, IE 11, FireFox 46 | NA
| CARBON-85 | Searching for account issues in Leads section |  | Vivek | Working as expected | Working as expected | Google Chrome, IE 11, FireFox 46 | NA
| CARBON-169 | Balance Transfer 'Submit' issue in Finance tab |  | Vivek | Working as expected | Working as expected | Google Chrome, IE 11, FireFox 46 | NA
Sprint-78 | CARBON-103 | Sorting issue on Leads reports page for status column |  | Abhay | Working as expected | Working as expected | Google Chrome, FireFox. | NA
| CARBON-126 | "Duration" column sorting issue in "Call Tracking" section |  | Vivek | Working as expected | Working as expected | Google Chrome, FireFox. | NA
| AgileZen#325 | After editing partner in Valencia the list should remain as it is with the edited one. |  | Vivek | Working as expected | Working as expected | Google Chrome, FireFox. | NA
| CARBON-147 | Data missing on Billing History reports UI but present in downloaded CSV file. |  | Abhay | Working according to the ticket, but found a defect related to that page. | Working as expected | Google Chrome, FireFox. | Yes
| CARBON-94 | Sorting GUI Issues in Task Fulfillment and PPC Performance |  | Vivek | Found a defect in the ticket in its working. | Was not pushed to QA. | Google Chrome, FireFox. | Yes, Twice | Even after fixing it second time, the defect was reproduced. | Defect_Report_CARBON-94
| CARBON-328 | Lead Report Custom Date Range |  | Om | Found a defect in the ticket in its working. | Working as expected | Google Chrome, FireFox. | Yes |  | Defect_Report_CARBON-328
| CARBON-359 | Accounts Status Reordering |  | Abhay | Working as expected | Working as expected | Google Chrome, FireFox. | NA
| CARBON-356 | OS Valencia: Super Admin Highlight and Sort |  | Vivek | Partially tested. Raised query against the color chosen. | Basic functionality working as expected. | Google Chrome, FireFox. | NA
Sprint-79 | CARBON-365 | OS Carbon: Advertiser Account Welcome Email Content Change |  | Vivek | Working as expected |  | Google Chrome
| CARBON-367 | OS Carbon: Remove Main Partner from “Attach Partner Property” Dropdown | After fixing it after 4th time tested it on Harsh's VM.(to avoid rework) | Harsh | Found a defect in the working functionality of the page. |  | Google Chrome | Yes, discussed with client also. Found one more defect. | When you select one of partner accounts of safeguard then what should be the scenario. I.e what should you be able to view in the dropdown. | Defect_Report_CARBON-367 | Yes raised a ticket after fixing the defect 2nd time. | Defect_Report_CARBON-367 | Yes raised a ticket after fixing the defect 3rd time. | Defect_Report_CARBON-367_V2 | Yes raised a ticket after fixing the defect 4th time. | Defect_Report_CARBON-367_V3 | Even after testing it four times found a defect. | After fixing it for 4th time tested on Harsh VM machine before pushing to dev. (To avoid rework)
| CARBON-368 | OS Carbon: “Attach to Partner Property” Dropdown Permissions | After fixing it twice tested it on Harsh's VM.(to avoid rework) | Harsh | Found a defect in working functionality of the page. |  | Google Chrome | Yes, Twice. |  | Defect_Report_CARBON_368 | Yes raised a ticket after fixing the defect 2nd time. | Defect_Report_CARBON_368_V2 | [5 empty] | After fixing it for 4th time tested on Harsh VM machine before pushing to dev. (To avoid rework)
| CARBON-34 | Page keeps on loading when duplicate email id is entered. |  | Abhay | Working as expected | Working as expected | Google Chrome | Yes. But its not related to the expected working of ticket. Related to User page. |  | Defect_Report_CARBON-34
| CARBON-171 | Issue with editing account, State dropdown has no value and Country dropdown not proper. |  | Abhay | Working as expected | Working as expected | Google Chrome
| CARBON-148 | Filter by selection throwing error and not working properly on Import SEO Details under Tools tab |  | Vivek |  |  | Google Chrome
| CARBON-154 | Client Numbers: Existing client number should be edited/deleted without throwing any error | Was not able to reproduce as it was related to account which was deleted. | Vivek |  |  | Google Chrome | Yes. But its not related to the expected working of ticket. Related to another account on the same page. | While testing it with other scenarios could not find any client numbers under 74023, as they are already deleted. So not able to understand the actual working of the defect.
Sprint-80 | CARBON-369 | OS Carbon: Price and Cost Changes |  | Om & Abhay
| CARBON-381 | OS Valencia: Roadmap Admin Number |  | Harsh
| CARBON-382 | OS Valencia: Case Admin Number |  | Harsh